## Project
Story | Name | Start Date | End Date | Days Used
123314 | Alwarsamy, Chandru (RT-CON) | 2021-07-09 | 2021-07-13 | 2 | 1
123315 | Han, George (RT-CON) | 2021-07-07 | 2021-07-13 | 4 | 1
123316 | Alwarsamy, Chandru (RT-CON) | 2021-07-07 | 2021-07-13 | 4 | 2
124284 | Soundararajan, Deepika (RT-CON) | 2021-07-06 | 2021-07-19 | 9 | 2
123316 | Alwarsamy, Chandru (RT-CON) | 2021-07-07 | 2021-07-20 | 9 | 8
123314 | Alwarsamy, Chandru (RT-CON) | 2021-07-09 | 2021-07-16 | 5 | 9
122058 | Imboden, Tom (RT-PHL) | 2021-07-07 |  |  | 3
124285 | Soundararajan, Deepika (RT-CON) | 2021-07-06 | 2021-07-20 | 10 | 1
123288 | Michalev, Sergey (RT-CON) | 2021-07-09 | 2021-07-13 | 2 | 1
123273 | Han, George (RT-CON) | 2021-07-13 | 2021-07-23 | 8 | 2
123286 | Polisetty, Sravya (RT-CON) | 2021-07-15 | 2021-08-03 | 17 | 2
123313 | Polisetty, Sravya (RT-CON) | 2021-07-12 | 2021-07-26 | 10 | 1
123270 | Singh, Harinder (RT-CON) | 2021-07-12 | 2021-07-20 | 6 | 1
123271 | Alwarsamy, Chandru (RT-CON) | 2021-07-13 | 2021-07-14 | 1 | 6
123274 | Polisetty, Sravya (RT-CON) | 2021-07-15 | 2021-07-26 | 7 | 8
124501 | Alwarsamy, Chandru (RT-CON) | 2021-07-14 | 2021-07-19 | 3 | 10
123286 | Polisetty, Sravya (RT-CON) | 2021-07-15 | 2021-08-03 | 13 | 5
123313 | Polisetty, Sravya (RT-CON) | 2021-07-12 | 2021-08-03 | 16 | 3
124505 | Turner. Todd (RT-CON) | 2021-07-16 | 2021-07-28 | 8 | 1
124503 | Alwarsamy, Chandru (RT-CON) | 2021-07-19 | 2021-07-19 | 0 | 11
124280 | Imboden, Tom (RT-PHL) | 2021-07-21 | 2021-07-24 | 1 | 1
124707 | Alwarsamy, Chandru (RT-CON) | 2021-07-20 | 2021-07-22 | 2 | 3
122061 | Alwarsamy, Chandru (RT-CON) | 2021-07-20 | 2021-07-23 | 1 | 4
124812 | Dixon, Reggie (RT-CON) | 2021-07-23 | 2021-07-30 | 5 | 1 | Collabera
124814 | Alwarsamy, Chandru (RT-CON) | 2021-07-23 | 2021-07-26 | 1 | 12
124708 | Singh, Harinder (RT-CON) | 2021-07-23 | 2021-07-28 | 3 | 2
124764 | Singh, Harinder (RT-CON) | 2021-07-22 | 2021-07-28 | 4 | 3
124767 | Paudel, Jagan (RT-CON) | 2021-07-22 | 2021-07-28 | 4 | 1
124766 | Han, George (RT-CON) | 2021-07-23 | 2021-07-29 | 4 | 3
124282 | Polisetty, Sravya (RT-CON) | 2021-07-24 | 2021-07-26 | 1 | 4
124363 | Polisetty, Sravya (RT-CON) | 2021-07-24 | 2021-07-26 | 1 | 6
124663 | Alwarsamy, Chandru (RT-CON) | 2021-07-20 | 2021-07-23 | 1 | 7
124586 | Alwarsamy, Chandru (RT-CON) | 2021-07-20 | 2021-07-21 | 1 | 5
124649 | Bashar, Habibul (LNG-CON) | 2021-07-22 | 2021-07-30 | 6 | 1
124500 | Imboden, Tom (RT-PHL) | 2021-07-19 |  |  | 4
124499 | Polisetty, Sravya (RT-CON) | 2021-07-22 | 2021-07-30 | 6 | 7
124504 | Imboden, Tom (RT-PHL) | 2021-07-19 |  |  | 5
124765 | Michalev, Sergey (RT-CON) | 2021-07-26 | 2021-07-27 | 1 | 2
124851 | Alwarsamy, Chandru (RT-CON) | 2021-07-26 | 2021-07-29 | 3 | 13
124844 | Singh, Harinder (RT-CON) | 2021-07-26 | 2021-07-28 | 2 | 4
124847 | Turner. Todd (RT-CON) | 2021-07-27 | 2021-07-29 | 2 | 2
124849 | Polisetty, Sravya (RT-CON) | 2021-07-26 | 2021-07-28 | 2 | 9
124813 | Han, George (RT-CON) | 2021-07-27 | 2021-07-29 | 2 | 4
124845 | Paudel, Jagan (RT-CON) | 2021-07-27 | 2021-08-02 | 4 | 2
124869 | McCardell, Robert (LNG-CON) | 2021-07-27 | not done |  | 0
124850 | Michalev, Sergey (RT-CON) | 2021-07-28 | 2021-08-05 | 6 | 3
124900 | Polisetty, Sravya (RT-CON) | 2021-07-28 | 2021-08-02 | 3 | 10
124852 | Alwarsamy, Chandru (RT-CON) | 2021-07-29 | 2021-07-31 | 2 | 14
124277 | Turner. Todd (RT-CON) | 2021-07-29 | 2021-08-10 | 8 | 3 | Collabera
124846 | Singh, Harinder (RT-CON) | 2021-07-29 | 2021-08-02 | 2 | 5
124898 | Carson, James (RT-CON) | 2021-07-29 | 2021-08-04 | 4 | 1
124852 | Alwarsamy, Chandru (RT-CON) | 2021-07-29 |  |  | 15
124930 | McCardell, Robert (LNG-CON) | 2021-07-29 | 2021-08-05 | 5 | 1
124848 | Han, George (RT-CON) | 2021-07-30 | 2021-08-01 | 2 | 5
124899 | Bashar, Habibul (LNG-CON) | 2021-07-31 | 2021-08-04 | 2 | 2
124812 | Singh, Harinder (RT-CON) | 2021-07-30 | 2021-08-03 | 2 | 6
124649 | Smith, David (RT-PHL) | 2021-07-30
124927 | Polisetty, Sravya (RT-CON) | 2021-07-31 |  |  | 11
124993 | Alwarsamy, Chandru (RT-CON) | 2021-08-02 | 2021-08-03 | 1 | 16
124679 | Han, George (RT-CON) | 2021-08-02 | On hold |  | 6
124992 | Paudel, Jagan (RT-CON) | 2021-08-02 | 2021-08-11 | 7 | 3
122067 | Paudel, Jagan (RT-CON) | 2021-08-06 | 2021-08-09 | 3 | 4
124290 | Carson, James (RT-CON) | 2021-08-02 | 2021-08-04 | 2 | 2
122066 | Alwarsamy, Chandru (RT-CON) | 2021-08-02 |  |  | 17
124331 | Abduvaliev, Akhror (LNG-CON) | 2021-08-03 | 2021-08-11 | 6 | 1
125037 | Han, George (RT-CON) | 2021-08-03 | 2021-08-04 | 1 | 7 |  | Closed
124957 | Polisetty, Sravya (RT-CON) | 2021-08-03 |  |  | 12
124985 | Singh, Harinder (RT-CON) | 2021-08-03 | 2021-08-12 |  | 7
124370 | Carson, James (RT-CON) | 2021-08-04 | 2021-08-30 | 16 | 3
124765 | Han, George (RT-CON) | 2021-08-04 | 2021-08-06 |  | 8
124989 | Michalev, Sergey (RT-CON) | 2021-08-04 | On hold |  | 4
124954 | Alwarsamy, Chandru (RT-CON) | 2021-08-06 |  |  | 3
124364 | Paudel, Jagan (RT-CON) | 2021-08-04 | 2021-08-13 | 7 | 5
122060 | Han, George (RT-CON) | 2021-08-05 | 2021-08-07 | 2 | 9
125058 | Bashar, Habibul (LNG-CON) | 2021-08-05 |  |  | 3 | Collabera
124990 | Michalev, Sergey (RT-CON) | 2021-08-05 | On hold |  | 5
122072 | McCardell, Robert (LNG-CON) | 2021-08-05 | 2021-08-11 | 4 | 2
124362 | Michalev, Sergey (RT-CON) | 2021-08-06 | 2021-08-09 | 1 | 6
125147 | Abduvaliev, Akhror (LNG-CON) | 2021-08-08 | 2021-08-11 | 3 | 2
125146 | Alwarsamy, Chandru (RT-CON) | 2021-08-09
125148 | Han, George (RT-CON) | 2021-08-09 | 2021-08-11 | 2 | 10 |  | Done
125149 | Michalev, Sergey (RT-CON) | 2021-08-09 | 2021-08-12 | 3 | 7 |  | Closed
122071 | Michalev, Sergey (RT-CON) | 2021-08-11 | 2021-08-13 | 2 | 8
125141 | Paudel, Jagan (RT-CON) | 2021-08-11 | 2021-08-16 | 5 | 6
125157 | Paudel, Jagan (RT-CON) | 2021-08-09 | 2021-08-16 | 7 | 7
125153 | Carson, James (RT-CON) | 2021-08-10 | 2021-08-12 | 2 | 4
125152 | Alwarsamy, Chandru (RT-CON) | 2021-08-10
125158 | Imboden, Tom (RT-PHL) | 2021-08-10
122064 | Polisetty, Sravya (RT-CON) | 2021-08-10
125145 | Han, George (RT-CON) | 2021-08-11 | 2021-08-15 | 4 | 11
125272 | Alwarsamy, Chandru (RT-CON) | 2021-08-11
125154 | Abduvaliev, Akhror (LNG-CON) | 2021-08-10 | 2021-08-13 | 3 | 3
125156 | McCardell, Robert (LNG-CON) | 2021-08-11 | 2021-08-12 |  | 3 |  | Closed
125296 | Abduvaliev, Akhror (LNG-CON) | 2021-08-11 | 2021-08-11 | 0 | 4 |  | Closed
125142 | Koranteng, Isaac (RT-CON) | 2021-08-11 |  |  | 1 |  | ???
125253 | Carson, James (RT-CON) | 2021-08-11 |  |  | 5
125262 | Singh, Harinder (RT-CON) | 2021-08-11 | 2021-08-17 | 4 | 8
125340 | Han, George (RT-CON) | 2021-08-12 | 2021-08-15 | 3 | 12
125335 | Abduvaliev, Akhror (LNG-CON) | 2021-08-12 | 2021-08-17 | 3 | 5
125325 | Michalev, Sergey (RT-CON) | 2021-08-12 | 2021-08-19 | 5 | 9
125151 | Paudel, Jagan (RT-CON) | 2021-08-12 | 2021-08-16 | 4 | 8
125155 | Paudel, Jagan (RT-CON) | 2021-08-13 | 2021-08-16 | 3 | 9
124986 | Abduvaliev, Akhror (LNG-CON) | 2021-08-15 | 2021-08-16 | 1 | 6
124988 | McCardell, Robert (LNG-CON) | 2021-08-12 | 2021-08-16 | 2 | 4
125196 | Alwarsamy, Chandru (RT-CON) | 2021-08-13
124987 | McCardell, Robert (LNG-CON) | 2021-08-15 | 2021-08-19 | 3 | 5
125444 | Han, George (RT-CON) | 2021-08-16 | 2021-08-18 | 2 | 13
125254 | Alwarsamy, Chandru (RT-CON) | 2021-08-16
125443 | Paudel, Jagan (RT-CON) | 2021-08-16 | 2021-08-18 | 2 | 10
125264 | Michalev, Sergey (RT-CON) | 2021-08-16 | 2021-08-18 | 2 | 10 |  | Closed
125442 | Singh, Harinder (RT-CON) | 2021-08-16 | 2021-08-18 | 2 | 9
125441 | Han, George (RT-CON) | 2021-08-17 | 2021-08-21 |  | 14
125519 | Han, George (RT-CON) | 2021-08-17 | 2021-08-18 | 1 | 15 |  | Closed
125535 | Han, George (RT-CON) | 2021-08-17 | 2021-08-23 | 6 | 16
124991 | Paudel, Jagan (RT-CON) | 2021-08-17 | 2021-08-20 | 3 | 11
125440 | Han, George (RT-CON) | 2021-08-18 |  |  | 17
125575 | Han, George (RT-CON) | 2021-08-18 |  |  | 18
125578 | Singh, Harinder (RT-CON) | 2021-08-18 | 2021-08-23 | 3 | 10
125252 | Alwarsamy, Chandru (RT-CON) | 2021-08-10
124994 | Michalev, Sergey (RT-CON) | 2021-08-18 | 2021-08-19 | 1 | 11
124287 | McCardell, Robert (LNG-CON) | 2021-08-18 | 2021-08-26 | 6 | 6 | Collabera
125579 | Paudel, Jagan (RT-CON) | 2021-08-18 | 2021-08-20 | 2 | 12
124653 | Paudel, Jagan (RT-CON) | 2021-08-19 | 2021-08-23 | 2 | 13
125338 | Abduvaliev, Akhror (LNG-CON) | 2021-08-17 | 2021-08-21 | 4 | 7
124244 | Abduvaliev, Akhror (LNG-CON) | 2021-08-18 | 2021-08-23 | 3 | 8
124245 | Michalev, Sergey (RT-CON) | 2021-08-20 | 2021-08-24 | 2 | 12
125655 | Han, George (RT-CON) | 2021-08-20 |  |  | 19
124680 | Alwarsamy, Chandru (RT-CON) | 2021-08-20
125572 | Abduvaliev, Akhror (LNG-CON) | 2021-08-22 |  |  | 9 | Collabera
124660 | Paudel, Jagan (RT-CON) | 2021-08-19 | 2021-08-26 |  | 14
125646 | Alwarsamy, Chandru (RT-CON) | 2021-08-19
124246 | Han, George (RT-CON) | 2021-08-23 | 2021-08-24 | 1 | 20
124248 | Koranteng, Isaac (RT-CON) | 2021-08-23 |  |  | 2 | Collabera
124681 | Alwarsamy, Chandru (RT-CON) | 2021-08-23
125684 | Han, George (RT-CON) | 2021-08-24 | 2021-08-26 | 2 | 21
125685 | Han, George (RT-CON) | 2021-08-24 | 2021-08-27 | 3 | 22
125690 | Han, George (RT-CON) | 2021-08-24 |  |  | 23
124648 | Paudel, Jagan (RT-CON) | 2021-08-24 |  |  | 15
125637 | Michalev, Sergey (RT-CON) | 2021-08-24 | 2021-08-26 | 2 | 13
125614 | Paudel, Jagan (RT-CON) | 2021-08-24 |  |  | 16
124128 | Koranteng, Isaac (LNG-CON) | 2021-08-23
125452 | McCardell, Robert (LNG-CON) | 2021-08-25 |  |  | 7
125720 | Han, George (RT-CON) | 2021-08-25 | 2021-08-27 | 2 | 24
125632 | Carson, James (RT-CON) | 2021-08-25 |  |  | 6
125760 | Paudel, Jagan (RT-CON) | 2021-08-26 |  |  | 17
125733 | Elangovan Ayyandurai | 2021-08-26 | 2021-08-31 | 3 | 1
125736 | Michalev, Sergey (RT-CON) | 2021-08-26 | 2021-08-31 | 3 | 14
125735 | Thi Nhat Van Le | 2021-08-27 |  |  | 1
125740 | Alwarsamy, Chandru (RT-CON) | 2021-08-26
125741 | Alwarsamy, Chandru (RT-CON) | 2021-08-27
125735 | Thi Nhat Van Le | 2021-08-27 |  |  | 2
125738 | Zarir Modegarian | 2021-08-27 | 2021-08-31 | 2 | 1
125439 | Han, George (RT-CON) | 2021-08-30 |  |  | 25
125613 | Han, George (RT-CON) | 2021-08-30 | 2021-08-31 | 1 | 26
125645 | Han, George (RT-CON) | 2021-08-31 | 2021-09-01 |  | 27
125451 | Michalev, Sergey (RT-CON) | 2021-08-24 | 2021-08-31 |  | 15
125640 | Carson, James (RT-CON) | 2021-08-31 |  |  | 7 | Collabera
125633 | Michalev, Sergey (RT-CON) | 2021-08-31 | 2021-08-31 |  | 16
125445 | Paudel, Jagan (RT-CON) | 2021-08-31 |  |  | 18 | Collabera
125454 | Zarir Modegarian | 2021-08-31 |  |  | 2
125641 | Zarir Modegarian | 2021-08-31 |  |  | 3
125554 | Zarir Modegarian | 2021-09-01 |  |  | 4
125608 | Zarir Modegarian | 2021-09-01 |  |  | 5
125636 | Elangovan Ayyandurai | 2021-08-31 |  |  | 2
125638 | Abduvaliev, Akhror (LNG-CON) | 2021-09-02 |  |  | 10
124251 | Michalev, Sergey (RT-CON) | 2021-09-02 |  |  | 17 | Collabera
125556 | Paudel, Jagan (RT-CON) | 2021-09-01 |  |  | 19 | Collabera
125643 | Han, George (RT-CON) | 2021-09-02 |  |  | 28
125448 | Han, George (RT-CON) | 2021-09-03 |  |  | 29
125887 | Han, George (RT-CON) | 2021-09-03 |  |  | 30 | Collabera
Note on A44: Han, George (RT-CON): Angular
Note on A55: Han, George (RT-CON): C++
Note on A61: Han, George (RT-CON): This is a .NET Core App
Note on A71: Han, George (RT-CON): Sergey's story, Angular

## Report
Week | Story | Name | Sroty Point | Start Date | Progress | Expected | End Date | status | Comments
1 | 124766 | ePMAdminServices | 5 | 2021-07-23 | 100% |  | 2021-07-29 | Complete
| 124813 | ePMReportsPortal | 5 | 2021-07-27 | 100% |  | 2021-07-29 | Complete
| 124848 | CWUReport | 5 | 2021-07-30 | 100% |  | 2021-07-31 | Complete
2 | 124679 | fepBoxingService | 8 | 2021-08-02 | 30% | N/A |  | On hold | Aaron wants Hold
| 125037 | MailService | 5 | 2021-08-03 | 100% |  | 2021-08-04 | Complete
| 124765 | ePMAdminPortal | 3 | 2021-08-04 | 70% | 2021-08-06 |  | In Progress
| 122060 | OCRWrapper | 5 | 2021-08-05 | 30% | 2021-08-06 |  | In Progress
Note on B3: Han, George (RT-CON): Angular
Note on B4: Han, George (RT-CON): C++
Note on B6: Han, George (RT-CON): This is a .NET Core App
Note on B8: Han, George (RT-CON): Angular, Assigned by Aaron, Original by Sergey

## Team
No. | Name | On Boarding | Consultant Com | Title | Department | Company | Manager | Work Phone | Home | Cell Phone | email | email legal
| Price, Terry (LNG-HPA) |  |  | Administrative Assistant III | SW Development Administration (86161) | Reed Technology Info. Services |  | 2157346538 |  | 215-734-6538 | TPrice@reedtech.com | PRICET1@legal.regn.net
| O'Boyle, Julianna (LNG-HPA) |  |  | Architect | SW Development QA (86159) | Reed Technology Info. Services | Stoneback, Don (LNG-HPA) | 2157346518 |  | 2679610313 | joboyle@reedtech.com
| Gillon, Patty (LNG-HPA) |  |  | Program Manager | SW Development Administration (86161) | Reed Technology and Info Serv |  |  |  | 267-688-1034
| Simpson, Tabatha (LNG-HPA) |  |  | Software Engineer III | SW Development QA (86159) | Reed Technology Info. Services | Mondelblatt, Aaron |  |  |  | tsimpson@reedtech.com
| Rosales, TJ P. (REPH-MNL ) |  |  | LN Service Desk - Web Developer I | PSS RETS Service Desk (PH440) | Reed Elsevier Shared Services (Philippines) Inc.
1 | Mondelblatt, Aaron |  |  | Mgr Software Engineering | SW Development Administration (86161) | Reed Technology Info. Services | Woeller, Raymond (LNG-HPA) | 2154416377 |  | 215 4416377 | AMondelblatt@reedtech.com | MONDELAJ@legal.regn.net
2 | Imboden II, Thomas M. (LNG-HPA) |  |  | Consulting SWE | SW Development QA (86159) | Reed Technology Info. Services | Mondelblatt, Aaron |  | 2157342134 | 2676881058 | timboden@reedtech.com
3 | Yang, Bing (LNG-HPA) |  |  | Sr DBA | SW Development QA (86159) | Reed Technology Info. Services | Mondelblatt, Aaron | 2676881057 | 215 4416400
4 | Stanley, Anthony (LNG-HPA) |  |  | Mgr Quality Eng | SW Development Administration (86161) | Reed Technology Info. Services | Woeller, Raymond (LNG-HPA)
5 | Smith, David (LNG-HPA) |  |  | Consulting Software Engineer | SW Development QA (86159) | Reed Technology Info. Services | Stoneback, Don (LNG-HPA) | 2154416400 | 2154416472
6 | Rubin, Milena (LNG-HPA) |  |  | Sr Project Manager | Admin-CIO/Comm Solutions (86115) | Reed Technology and Info Serv | Gibson, Theresa (LNG-HPA) | 2156828292 | 2156828292
7 | McBride, Katie A. (LNG-HPA) |  |  | Sr Quality Test Analyst | SW Development QA (86159) | Reed Technology Info. Services
8 | Calnek, Steve (LNG-HPA) |  |  | Senior Software Engineer | SW Development QA (86159) | Reed Technology Info. Services
9 | Alwarsamy, Chandru (LNG-CON) |  |  | Contractor Analyst III Contractor | SW Development QA (86159) | Reed Technology and Info Serv | Mondelblatt, Aaron
10 | Polisetty, Sravya (RT-CON) |  |  | Contractor Analyst III Contractor | SW Development QA (86159) | SW Development QA (86159) | Mondelblatt, Aaron
11 | Singh, Harinder (LNG-CON) |  |  | Contractor Analyst III Contractor | SW Development QA (86159) | Reed Technology and Info Serv | Mondelblatt, Aaron
12 | Han, Gaogao (LNG-CON) | 2021-07-06 | Collabera | Contingent Worker Default | SW Development Administration (86161) | Reed Technology and Info Serv
13 | Michalev, Sergey (LNG-CON) | 2021-07-06 | Collabera | Contingent Worker Default | SW Development Administration (86161) | Reed Technology and Info Serv | Woeller, Raymond (LNG-HPA) |  | 8186441033
14 | Turner, Todd (LNG-CON) | 2021-07-06 | Collabera | Contingent Worker Default | SW Development Administration (86161) | Reed Technology Info. Services | Woeller, Raymond (LNG-HPA)
15 | Bashar, Habibul (LNG-CON) | 2021-07-16 | Collabera | Contingent Worker Default | SW Development Administration (86161) | Reed Technology and Info Serv | Woeller, Raymond (LNG-HPA)
16 | Patel, Atul (LNG-CON) | 2021-07-16 | Collabera | Contingent Worker Default | SW Development Administration (86161) | Reed Technology and Info Serv | Woeller, Raymond (LNG-HPA)
17 | Hoque, Syed (LNG-CON) | 2021-07-06 | Collabera | Contingent Worker Default | SW Development Administration (86161) | Reed Technology and Info Serv | Woeller, Raymond (LNG-HPA) |  |  | 9177415332
18 | Cole, Bryar (LNG-CON) | 2021-07-16 | Collabera | Contingent Worker Default | SW Development Administration (86161) | Reed Technology and Info Serv | Woeller, Raymond (LNG-HPA)
19 | Onal, Omer (LNG-CON) | 2021-07-16 |  | TEMP-Outside Agency Contractor | SW Development Administration (86161) | Reed Technology and Info Serv | Woeller, Raymond (LNG-HPA)
20 | Islam, Mohammad (LNG-CON) | 2021-07-16 | Collabera | Contingent Worker Default | SW Development Administration (86161) | Reed Technology and Info Serv | Woeller, Raymond (LNG-HPA)
21 | Ahmed, Saquib (LNG-CON) | 2021-07-16 |  | Contingent Worker Default | SW Development Administration (86161) | Reed Technology and Info Serv | Woeller, Raymond (LNG-HPA)
22 | Soundararajan, Deepika (LNG-CON) |  |  | Contractor Analyst III Contractor | SW Development QA (86159) | SW Development QA (86159)
23 | Dixon, Reggie (LNG-CON) |  |  | Contingent Worker Default | SW Development Administration (86161) | Reed Technology and Info Serv
24 | McCardell, Robert (LNG-CON) | 2021-07-23 | Collabera | TEMP-Outside Agency Contractor | SW Development Administration (86161) | Reed Technology and Info Serv
25 | Paudel, Jagan (LNG-CON) | 2021-07-23 | Collabera | Contingent Worker Default | SW Development Administration (86161) | Reed Technology and Info Serv
26 | Carson, James (LNG-CON) | 2021-07-21 | Collabera | Contingent Worker Default | SW Development Administration (86161) | Reed Technology and Info Serv
27 | Abduvaliev, Akhror (LNG-CON) | 2021-08-01 | Collabera | TEMP-Outside Agency Contractor | SW Development Administration (86161) | Reed Technology and Info Serv
28 | Koranteng, Isaac (LNG-CON) | 2021-08-09 | Collabera | Contractor Analyst III Contractor | SW Development QA (86159) | Reed Technology and Info Serv
29 | Modegarian, Zarir (LNG-CON) | 2021-08-23 | Collabera | Contingent Worker Default | SW Development Administration (86161) | Reed Technology and Info Serv
30 | Thi Nhat Van Le | 2021-08-23
Elangovan Ayyandurai
| Mangalan, Anoop |  | Collabera | Senior Engineering Manager | [6 empty] | anoop.mangalan@collabera.com
| Gopinath, Rajeev |  | Collabera | [7 empty] | rajeev.gopinath@collabera.com
| Fisher, Erika |  | Collabera | Account Manager | [6 empty] | erika.fisher@collabera.com
Note on H3: Han, George (RT-CON): Mgr and Chief Architect
Note on H12: Han, George (RT-CON): Sr Dir SW Dev Group
Note on H16: Han, George (RT-CON): Mgr and Chief Architect
Note on H17: Han, George (RT-CON): Manager, Program Management Office
Note on B27: Han, George (RT-CON): Leave since 8/10
Note on B28: Han, George (RT-CON): leave 8/11

## Project Status
George's Weekly Report
Week | Finished Stories | Story | Story Name | Point | Start Date | Progress | Expected | End Date | status | Comments
Current | 2 | 125906 | Cwu2Xml (DLL) | 2 | 2021-09-07 | 100% | 2021-09-10 | 2021-09-09 | Complete |  | 32
|  | 125902 | ExtractPTOTarExport | 2 | 2021-09-07 | 100% | 2021-09-10 | 2021-09-08 | Complete |  | 31
|  | 125887 | Error Pop Up | bug fix | 2021-09-03 |  | 2021-09-10 |  |  |  | 30
|  | 125448 | fepBoxing | 5 | 2021-09-03 | 90% | 2021-09-10 |  | In progress | only need yaml | 29
|  | 125643 | MoveBoxes | 5 | 2021-09-02 | 100% | 2021-09-07 | 2021-09-07 | Complete |  | 28
|  | 124679 | fepBoxingService | 8 | 2021-08-02 | 30% | 2021-09-10 |  | In progress | Aaron made it on Hold | 6
6 | 5 | 125645 | fepImageRotate | 5 | 2021-08-31 | 100% | 2021-09-02 | 2021-09-02 | Complete |  | 27
|  | 125613 | fepIfwPackagesXmlExtract | 5 | 2021-08-30 | 100% | 2021-09-01 | 2021-08-31 | Complete |  | 26
|  | 125439 | SideBySidePs2TifViewer | 5 | 2021-08-30 | 100% | 2021-09-01 | 2021-09-03 | Complete |  | 25
|  | 125690 | App does NOT launch | bug fix | 2021-08-24 | 100% | 2021-08-27 | 2021-09-01 | Complete | WCF disable | 23
|  | 125655 | Cannot access Text QC Left hand panel | bug fix | 2021-08-20 | 100% | 2021-08-25 | 2021-08-31 | Complete | Access issue | 19
5 | 5 | 125720 | Star Toolbox generates error | bug fix | 2021-08-25 | 100% | 2021-08-27 | 2021-08-26 | Complete | Closed | 24
|  | 125685 | IDCBilling - Replace EPPlus | 5 | 2021-08-24 | 100% | 2021-08-27 | 2021-08-27 | Complete | Assign to Tabatha | 22
|  | 125684 | RTFMWS - Replace EPPlus | 5 | 2021-08-24 | 100% | 2021-08-26 | 2021-08-25 | Complete |  | 21
|  | 124246 | FepScoreScoresSupport (fepScoreWs) | 5 | 2021-08-23 | 100% | 2021-08-25 | 2021-08-24 | Complete | Assign to Dave | 20
|  | 125535 | RTFM loader fails to | bug fix | 2021-08-17 | 100% | 2021-08-19 | 2021-08-23 | Complete | To Niles | 16
4 | 5 | 125575 | move TimeTracker.Tests | 2 | 2021-08-18 | 100% | 2021-08-20 | 2021-08-19 | Complete | Closed | 18
|  | 125440 | StarToolbox | 5 | 2021-08-18 | 100% | 2021-08-20 | 2021-08-21 | Complete | Closed | 17
|  | 125519 | Update RTFM loader config email | Bug fix | 2021-08-17 | 100% | 2021-08-19 | 2021-08-18 | Complete | Closed | 15
|  | 125441 | Tempus | 5 | 2021-08-17 | 100% | 2021-08-19 | 2021-08-21 | Complete | move to Tom | 14
|  | 125444 | YB2RipXps | 5 | 2021-08-16 | 100% | 2021-08-18 | 2021-08-18 | Complete | Kelly | 13
3 | 3 | 125340 | RTFMLoader | 8 | 2021-08-12 | 100% | 2021-08-16 | 2021-08-15 | Complete |  | 12
|  | 125145 | ePMLenTablesOCRQueue | 5 | 2021-08-11 | 100% | 2021-08-13 | 2021-08-15 | Complete | Conditional Pass | 11
|  | 125148 | epmRelHoldPS | 5 | 2021-08-09 | 100% | 2021-08-11 | 2021-08-11 | Complete | Closed | 10
2 | 3 | 122060 | OCRWrapper | 5 | 2021-08-05 | 100% | 2021-08-06 | 2021-08-07 | Complete | Closed | 9
|  | 124765 | ePMAdminPortal | 3 | 2021-08-04 | 100% | 2021-08-06 | 2021-08-06 | Complete | Move to Dave: NPM failed | 8
|  | 125037 | MailService | 5 | 2021-08-03 | 100% | N/A | 2021-08-04 | Complete | Closed | 7
1 | 3 | 124848 | CWUReport | 5 | 2021-07-30 | 100% | N/A | 2021-07-31 | Complete | Move to Tom | 5
|  | 124813 | ePMReportsPortal | 5 | 2021-07-27 | 100% |  | 2021-07-29 | Complete | Debugging | 4
|  | 124766 | ePMAdminServices | 5 | 2021-07-23 | 100% |  | 2021-07-29 | Complete | Moved to Dave | 3
-1 | 1 | 123273 | cofcCommentsCtl | 3 | 2021-07-13 | 100% |  | 2021-07-23 | Complete | Removed | 2
-2 | 1 | 123315 | epmQueries | 3 | 2021-07-07 | 100% |  | 2021-07-13 | Complete | Removed | 1
Note on D6: Han, George (RT-CON): Bug 3 to 125340
Note on C9: Author: This is a .NET Core App
Note on D12: Han, George (RT-CON): Local develop conflict If need redo, make a new local folder, then check out
Note on D14: Han, George (RT-CON): bug 125441
Note on D15: Han, George (RT-CON): Bug to 124813
Note on D17: Han, George (RT-CON): Bug 125440
Note on K20: Han, George (RT-CON): Web Service to Dave
Note on D21: Author: Bug 2 to 125340
Note on D23: Author: Modify structure for 124708, Harinder
Note on D25: Author: Bug 1 to 125340
Note on C34: Author: Angular, Assigned by Aaron, Original by Sergey
Note on C37: Author: C++
Note on C38: Author: Angular

## Collabera Team
No. | Team
1 | Mondelblatt, Aaron (LNG-HPA) <AMondelblatt@reedtech.com>;
2 | Burella-Wilkinson, Bethann N. (LNG-HPA) <BWilkinson@reedtech.com>;
3 | Calnek, Steve (LNG-HPA) <steve.calnek@reedtech.com>;
4 | Carnes, Terry B. (LNG-HPA) <Tcarnes@reedtech.com>;
5 | Desphy, Niles S (LNG-HPA) <ndesphy@reedtech.com>;
6 | Dupiche, Herve (LNG-HPA) <hdupiche@reedtech.com>;
7 | Gu, Jason (LNG-HPA) <jgu@reedtech.com>;
8 | Imboden II, Thomas M. (LNG-HPA) <timboden@reedtech.com>;
9 | Matro, Alexander (LNG-HPA) <AMatro@reedtech.com>;
10 | Megni, Lori (LNG-HPA) <LMegni@reedtech.com>;
11 | Miles, Alesha G. (LNG-HPA) <amiles@reedtech.com>;
12 | Morin, Nikita (LNG-HPA) <NMorin@reedtech.com>;
13 | Nixon, Jay V. (LNG-HBE) <jayvictor.nixon@lexisnexis.com>;
14 | Rottman, Gavin (LNG-HPA) <gavin.rottman@reedtech.com>; Simpson,
15 | Tabatha (LNG-HPA) <TSimpson@reedtech.com>;
16 | Soundararajan, Deepika (LNG-CON) <Deepika.Soundararajan@reedtech.com>;
17 | Timofeyev, Igor (LNG-HPA) <ITimofeyev@reedtech.com>;
18 | Veera Raajan, Suganya (LNG-HPA) <Suganya.Raajan@reedtech.com>;
19 | Yang, Bing (LNG-HPA) <Byang@reedtech.com>;
20 | Zhou, Jennifer (LNG-HPA) <hzhou@reedtech.com>;
21 | Abduvaliev, Akhror (LNG-CON) <Akhror.Abduvaliev@reedtech.com>;
22 | Alwarsamy, Chandru (LNG-CON) <Chandru.Alwarsamy@reedtech.com>;
23 | Bashar, Habibul (LNG-CON) <Habibul.Bashar@reedtech.com>;
24 | Carson, James (LNG-CON) <James.Carson@reedtech.com>;
25 | Feliccia, Nic (LNG-CON) <nic.feliccia@reedtech.com>;
26 | Kapu, Vani (LNG-CON) <Vani.Kapu@reedtech.com>;
27 | Kotamahanti, Satya Veda (LNG-CON) <SatyaVedaSirisha.Kotamahanti@reedtech.com>;
28 | McCardell, Robert (LNG-CON) <Robert.McCardell@reedtech.com>;
29 | Michalev, Sergey (LNG-CON) <Sergey.Michalev@reedtech.com>;
30 | Paes, Mario (LNG-CON) <mario.paes@reedtech.com>;
31 | Paudel, Jagan (LNG-CON) <Jagan.Paudel@reedtech.com>;
32 | Polisetty, Sravya (LNG-CON) <sravya.polisetty@reedtech.com>;
33 | Singh, Harinder (LNG-CON) <Harinder.Singh@reedtech.com>;
34 | Turner, Todd (LNG-CON) <Todd.Turner@reedtech.com>;
35 | Vallabaneni, Vyjayanthi (LNG-CON) <vyjayanthi.vallabaneni@reedtech.com>;
36 | Woelfel, Brian (LNG-CON) <brian.woelfel@reedtech.com>